## Sprint 1
Functional Testing Case Study - 1
Task/Scenario Given: |  | The following website is given for Manual Testing to follow Agile practices and design and execute Test Cases and create Defect Report https://freecrm.co.in/index.html
Sprint Day | Sprint Activity | Overview and scope of functionality
Sprint Day 1 | Project Management Activity: Product Owner 1. Create user stories based open functionality I. Understanding requirements II. Assign priority III. Assign user stories to team members 2. Identify the De+B3pendacy between the requirement 3. Final ordering of product backlog item( set of all user stories) Create Task / Deliverables: 1. List of User Stories & Functions to test 2. All tasks with JIRA should be ready in SCRUM template | Project Overview: Free CRM delivers cloud-based and as well as a full range of software and choice in how you want it - licensed, on-demand, private label, and custom services. In scope Functionality: A. Login Module 1. User should be able to Login to FreeCRM by entering valid credentials on Login Panel. B.Add a new company by entering required details i)Click on contacts and create New contacts by entering details. ii)Click on Deal tab and Create a new deal. iii)Click on Tasks tab and create new tasks iv)Veirfy on calender weather the created tasks are reflecting on calender page. Out of Scope Functionality: Load Testing and Security Testing on Leave Management System. Expected Implementations : 1. Usage of all Testing Types 2. Usage of Test Design Techniques like EP, BVA etc. 3. Usage of Valid invalid input data 4. Test case design in Integration and system level testing
Sprint Day 2 | JIRA Task and Test Design : Dev Team 1. Assign story point or time required to accomplish the story/Task 2. Categorize user stories in to Epic, User Stories, Tasks & SubTasks 3. Assign the stories to components 4. Add group members in th Project on JIRA. 5. Create MAnual Test Scenarios Create Task / Deliverables: 1. Test scenarios 2. Test Case design
Sprint Day 3 | Scrum Team activities : Dev Team 1. Create scrum based sprints 2. Create Sprint backlog (select the stories for the particular Sprint) 3. Create Sprint board (Todo , in process, Done) Create Task / Deliverables: 1. Test Case design 2. Test Case execution
Sprint Day 4 | Scrum Team Activity : Scrum Team (PO, SM, DT) 1. Plan for release 2. Generate Agile report relevant to scrum project (e.g. Burn down chart, Sprint report etc.) Create Task / Deliverables: 1. Defect reporting 2. Traceability Matrix 3. Test summary report Keep all the Deliverables on Git
Sprint Day 5 | Sprint Evaluation

## User Story
Issue type | Summary | Description
|  | Objective | Acceptance
Epic | Contact | This epic is related to UI of contact and functionality of contact and to create new contact.
Story | Ui of contact | As a registered User, I want to see the list of contacts. | 1.When users click on Contact Than there should be options like View, Show filters, Export and New. 2.Headings like Name, Address, Category, Status, Phone, Email, Options are mapped with already existed Contacts. 3.Sub-Options are used to View, Edit, Call and Delete the contact. 4.There should be checkbox in front of each contact. 5.If there is no contact is created it should display "No records found". 6.When click on new button ,it should create new contact. 7.At the bottom there should be a dropdown list of action having Delete value. Note : Beside it Correct sign button should be there so after clicking it will display the confirmation window of delete option.

## Test Scenario
Story name | TestScenarioID | Requirement ID | Test Scenario Description | Type of Testing | Possible No. of TestCases | Test Case Details
UI of Contact | TS_01 | COG-48 | To verify the Contact Button | UI testing | 1 | Check the contact button in Home page
| TS_02 |  | To verify Contact functionality | Functional | 1 | verify to click Contact button
| TS_03 |  | To verify the New | Functional | 1 | Verify to click of New Button

## Test Case
Test Case ID | Story/Folder | Objective | Precondition | Test Name | Test Case Steps | Priority | Test Data | Expected Result | Actual Result | Status
TC_CRM_001 | /UI for Contact | To verify the Contact | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid user and password. | Check the contact button in Home page | 1. Go to URL https://ui.freecrm.com/ 2.Loogin with valid username and password. | High |  | It should display the Contact button on left sidebar | It displays the contact button on left sidebar on home | Pass
TC_CRM_002 | /UI for Contact | To verify Contact functionality | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid user and password. 3.Contact button on left side. | verify the click of Contact button | 1. Go to URL https://ui.freecrm.com/ 2.Loogin with valid username and password. 3.Click on the Contact Button | HIgh |  | It should display the Contact page with various buttons like View, Exprt, Show filters and New and Action and all created contacts. | It displays the Contact Page with various button like View, Export, Show Filters and New and Action and already created contacts | Pass
TC_CRM_003 | /UI for Contact | To verify the New Button | 1.URL https://ui.freecrm.com/ should be working. 2.User should have valid user and password. 3.Contact button should be working. | Verify the click of New Button | 1. Go to URL https://ui.freecrm.com/ 2.Loogin with valid username and password. 3.Click on the Contact Button 4.Click on New Button | Normal |  | It should display a page to create new contact. | It displays a page with various fields to create new contact | Pass

## Defect Report
Defect ID | Summary | ReportedBy | Date | Assigned To | Severity | Priority | Status | Module | Build Version | Reproducable | ReproSteps
There is no bug

## Test Summary Report
Test Summary Report for Sprint1 (27 - Nov to 02-Dec )
S.No. | Activities | Count | Passed | Failed | Duplicate | Remarks
1 | Created User Stories | 10
2 | Created TestCases | 130
3 | No. of tests Executed in Sprint ,iteration 1 | 130 | 123 | 7
4 | Defects Reported | 6
5 | No. of Sprints Executed | 1
Any Challenges
Any Best Practises

## Burn Down Chart
BURN DOWN CHART

## Sprint Report
SPRINT REPORT